## Sheet1
type | id | feature | description | priority | estimation
userStory | US001 | Login and Registration | As a Visitor, I want to register for an account so that I can become a User. | High | 3
userStory | US002 | Viewing Content | As a User, I want to see blog posts and products on the website. | Medium | 5
userStory | US003 | Multilingual Support | As a User, I want to choose between English, French, or Arabic languages for the website. | Medium | 5
userStory | US004 | Content Management | As an Admin, I want to add and remove multimedia content such as photos and videos. | High | 8
userStory | US005 | Geolocation | As a User, I want a geolocation feature for the shop's checkout system. | High | 8
userStory | US006 | Electronic Payment | As a User, I want to make electronic payments using PayPal at checkout. | High | 10
userStory | US007 | Product Pages | As a User, I want detailed product pages that show product descriptions. | Medium | 5
userStory | US008 | Contact Form | As a User, I want a contact form with the shop's contact details at the bottom of the website. | Low | 3
userStory | US009 | Blog Post Approval | As an Admin, I want to approve blog posts submitted by users before they are published. | Medium | 5
userStory | US010 | Search Functionality | As a User, I want to search for products based on keywords. | Medium | 8
feature | F001 | Blog Management | Admin can manage blog posts. | High | 8
feature | F002 | Product Management | Admin can manage products. | High | 8
feature | F003 | Checkout Process | Implementing the checkout process with payment integration (e.g., PayPal). | High | 13
feature | F004 | Search Engine Optimization (SEO) | Optimize the code for better search engine visibility. | Medium | 10
feature | F005 | Profile Management | Allow users to edit and update their profiles. | Medium | 8
task | T001 | Create registration form. | Create registration form. | Low | 2
task | T002 | Implement user authentication. | Implement user authentication. | Medium | 4
task | T003 | Create admin interface for managing blog posts. | Create admin interface for managing blog posts. | Medium | 5
task | T004 | Create admin interface for managing products. | Create admin interface for managing products. | Medium | 5
task | T005 | Integrate PayPal for electronic payments. | Integrate PayPal for electronic payments. | High | 8
task | T006 | Implement blog post approval workflow. | Implement blog post approval workflow. | Medium | 5
task | T007 | Implement product search functionality. | Implement product search functionality. | High | 8
task | T008 | Implement SEO best practices in the code. | Implement SEO best practices in the code. | Medium | 10
task | T009 | Create user interface for profile management. | Create user interface for profile management. | Medium | 6